## Sheet1
Task | Sub Task | Dependency | Owner | Status | Due date | Notes/Issues
Capstone Schedule - Task List |  |  | Thong | Done | 2017-10-04 | Ongoing updates
Weekly Meeting Notes | https://docs.google.com/document/d/1IUTJGo2NP8Zyq8PR-mjt4UX-_vdo74YvDBApfbOP9oc/edit# |  | Thong | Ongoing |  | Ongoing updates
Workshop 1
| Scope |  | Thong | Done | 2017-10-03
| Schedule |  | Sarah | Done | 2017-10-03
Presentation 1 |  |  |  |  | 2017-10-10
| Draft Outline - slide 1-3 |  | Sarah | Done |  | Suggested Division of slides: Sarah (1-3);
| Slides 4-6 |  | Zhongqiao | Done
| Slides 7-8 |  | Shankar | Done
| Slides 9-10 |  | Thong | Done
| Get images and beautify |  | Thong | Done
| Post it |  | Thong | Done
Project Description to post on wall |  |  |  |  | 2017-10-10
| First Draft |  | Sarah | Done
| Edits |  | Thong, Shankar, Zhongqiao | Done
| Post |  | Thong | Done
Presentation 2 | Presentation Outline |  | Sarah | Done | 2017-11-09
| First Draft |  | All | Done
| Get images and beautify |  | Thong | Done
| Post |  | Thong | Done
--------------------------------------------------------------------------------------------------------------------------------------------------------------------------
1) Read ticker data for S&P stocks from Yahoo Finance |  |  | Thong | Done on 10/6 | 2017-10-06
| Full data dump (start date = 2000-01-01) |  |  | 100%
| Incremental data dump |  |  | 100%
| Unit test |  |  | 100%
| Check-in code, data |  |  | 100%
2) Read data from Twitter |  |  | Sarah | Done | 2017-10-06 | Not very useful because not histroical; can work on building in for real time updates
| Current and historical data? |  |  | 100%
| Unit test |  |  | 100%
| Check-in code, data |  |  | 100%
3) Read historical news |  |  | Zhongqiao | Done | 2017-10-08 | Only got data since 2010. Will try google API
| Full data dump (start date = 2015?) |  |  | 90% |  | Google api can get back as far as 2015
| Incremental data dump |  |  | 90%
| Flag: Q1, ... Q4, FY |  | Zhongqiao, Sarah |  | 2017-11-12
| Unit test |  |  | 100%
| Check-in code, data |  |  | 100%
4) Read revenue data about a company |  |  | Shankar | Done | 2017-10-08
| static data dump: company size, employees |  |  |  | 2017-10-12 | Comprehensive Data available via API from Datanyze or FullContact. But only 100 API calls per month are free, basic subscription fee of $99 per month allows up to 2500 calls per month
| 300 stocks |  | Shankar | Done | 2017-11-17
| Dividend, PE ratio (not historical), revenues (historical?) |  | Shankar, Thong | Done | 2017-10-08 | Revenue and Dividends done, searching for FREE historical PE ratio.
| Historical data - Full (start date = 2008) |  |  | complete for b'Date,Open,High,Low,Close,Volume,Dividend,Split,Adj_Open,Adj_High,Adj_Low,Adj_Close,Adj_Volume\n' based upon stock symbol | 2017-10-08 | Thong: where is the sp500 data? : No free data available. We can try to get data for $40 - $99 per month.
Have not found any free sites that offer Historical data
[5 empty] | 2017-10-08 | Basic client committed, works on specific ticker symbol, more development will happen in coming weeks
5) NLP on news |  |  |  | Done | 2017-11-06 | Must be done sooner than 11/10 to unblock baseline, final model
| sample output data |  | Zhongqiao | Done
| Remaining data (340) |  | Zhongqiao | Done | 2017-11-18
| Finalize feature extraction |  | Sarah |  | 2017-11-24 | Basic features for MVP, better features to come for next round
Unit test
Check-in code and data
6) UI (MVP) |  |  |  |  | 2017-11-10
| Basic Wireframes |  | Sarah | Done | 2017-10-23
| Review Wireframes |  | team | Done
| Basic Flask Apps |  | Sarah | Done | 2017-11-06 | MVP
| Code for basic flask app up on github (with local-ly runanble html files) |  | Sarah | Done | 2017-11-12
| Static HTML pages for main page explaining what and risks | None | Zhongqiao |  | TDB
| Basic formatting on interactive page | Code on github | Shankar |  | TBD
| Connect the flask to back end | 8,9 | Thong | Done | 2017-11-20
| Finished Flask Apps |  | Sarah/Thong | Done | 2017-12-01
| Improving UI |  | Thong | 50%
| Deploy App to AWS |  | Sarah | Done
| Automate git pull from AWS |  | Sarah
7) Baseline Model
| Build training and test data (just stock prices) |  | Thong | Done | 2017-10-15
| basic model with just price data | 1 | Thong | Done | 2017-10-20 | The current model is not good at prediction stock price. Will have to try others
| normalized data | 1 | Thong | Done | 2017-10-30
| Unit test |  | Thong | Done | 2017-10-30
| Check-in code |  | Thong | Done | 2017-10-30
8) Final Model |  |  |  |  | 2017-12-06
| LSTM model with just price data |  | Thong | Done
| price + other financial + NLP news data | 1,2,3, 5(?) | Thong | Done |  | This is the most laborious step to integrate and rerun everything
| identify stocks with highest returns |  | Thong | Done
| train & predict with 500 stocks (30, 45, 60 days) |  | Thong | Done
| Data Analysis to narrow down features to use |  | Thong | Done
| Tuning for overfitting |  | Thong | Done
| Unit test |  | Thong | Done
| Check-in code |  | Thong | Done
9) Use ML output to recommend portfolio given investor goals (given risk choice, 10% growth in 2 months) |  | 7,8 |  |  | 2017-11-30
| Output: top 10 list of stocks |  | Thong | Done
11) User evaluation |  |  | Sarah | Done | 2017-12-03